FDAS Alarm Notification System

Project Charter — team roles, tech stack, and delivery plan • Aug 9 – Sep 30

Project Overview

This charter operationalizes the approved FDAS Alarm Notification System proposal into a 6-person build across roughly 7.5 weeks. The system observes an existing, unmodified FDAS panel with a fixed camera, extracts the alarm's device code via OCR, and dispatches an SMS to the responsible personnel while permanently logging every event. It is a supplementary notification layer only — it does not modify, interface with, or replace the certified panel, hooters, or sirens. This document defines who owns which part of the 13-step pipeline, what tools the team will build with, and the week-by-week plan to a working, tested system by end of September.

Objectives & Success Criteria

●  Functional pipeline — all 13 steps from the proposal implemented and running end-to-end on the target hardware.

●  Reliable notification — SMS delivered within seconds of a real alarm, with retry/escalation on failure.

●  Complete audit trail — every detected event permanently logged, independent of SMS outcome.

●  Self-monitoring — watchdog correctly raises a distinct fault alert on camera or process failure.

●  Demonstrated reliability — a multi-day soak test with no missed or duplicate notifications before final submission.

Team & Roles

| Slot | Role | Owns | Key Deliverable |
| --- | --- | --- | --- |
| Member 1 | Hardware & Calibration Lead | Camera/lens mounting, anti-glare setup, ROI + LED-region calibration | Calibrated rig + calibration.json |
| Member 2 | CV / OCR Engineer | Steps 1-6: capture, LED detection, crop, preprocess, OCR, validation | detect_event() module |
| Member 3 | Backend / Pipeline Engineer | Steps 7-10: debounce, dedupe, location lookup, DB + logging | process_event() + DB schema |
| Member 4 | Notifications Engineer | Steps 11-12: SMS dispatch, retry/escalation, resolution tracking | send_notification() + resolve_event() |
| Member 5 | Reliability / DevOps Engineer | Step 13: watchdog, systemd services, deployment packaging | Running unattended service on Pi |
| Member 6 | QA / Integration / Docs (PM support) | Test rig, test plans, integration testing, documentation | Test suite + as-built docs |

Tech Stack

| Layer | Choice | Why |
| --- | --- | --- |
| Language | Python 3.11+ | Best library support for CV/OCR on a Raspberry Pi |
| Capture / CV | OpenCV | Frame grab, HSV thresholding, cropping, preprocessing |
| OCR | PaddleOCR (primary), Tesseract (fallback) | Matches the proposal's specified engines |
| Storage | SQLite (single panel) / PostgreSQL (multi-site) | SQLite is enough for one Pi; Postgres if centralizing logs |
| SMS | Twilio / cloud gateway API or SIM7600 GSM (pyserial) | Decide in Week 1 — affects hardware BOM and code |
| Process mgmt | systemd services + watchdog timer | Auto-restart on crash, matches the step-13 design |
| Config | YAML / JSON | Human-editable calibration + contact mapping, no code changes |
| Version control | Git + GitHub (private repo) | Branch per module: cv/, backend/, notify/, watchdog/ |
| Task tracking | GitHub Projects or Trello | Kanban board mirroring the 5 work blocks |
| Comms | Discord/Slack + weekly video standup | Async updates, one sync checkpoint per week |

Timeline & Milestones

| Week | Dates | Milestone |
| --- | --- | --- |
| Week 1 | Aug 9 – 15 | Kickoff, role sign-off, order hardware, GSM-vs-cloud decision, test rig started |
| Week 2 | Aug 16 – 22 | Hardware arrives + mounting begins; CV skeleton (capture, LED detect); DB schema drafted |
| Week 3 | Aug 23 – 29 | Calibration complete; OCR pipeline (crop → validate); notification prototype (hardcoded event) |
| Week 4 | Aug 30 – Sep 5 | Mid-project checkpoint, interfaces frozen; debounce + dedupe; watchdog v1 |
| Week 5 | Sep 6 – 12 | Location + event logging complete; full notify + resolve; first end-to-end integration |
| Week 6 | Sep 13 – 19 | Full integration testing; deployment packaging (systemd); bug-fix sprint |
| Week 7 | Sep 20 – 26 | Multi-day soak test on-site/simulated; documentation finalized |
| Final | Sep 27 – 30 | Final demo, submission, handoff |

Communication Plan

●  Weekly sync — one video standup per week; async updates in Discord/Slack the rest of the time.

●  Board — Kanban board with one column per work block (Hardware, CV, Backend, Notify, Reliability, QA).

●  Interface freeze — data contracts between modules (event object, DB schema, function signatures) locked at the Week 4 checkpoint.

●  Repo structure — one branch per module (cv/, backend/, notify/, watchdog/, hardware/), merged via pull request.

Risks & Mitigations

| Risk | Mitigation |
| --- | --- |
| Hardware shipping delay | Order in Week 1; start CV/backend dev against recorded test footage in parallel |
| GSM signal unreliable at site | Confirm coverage early; keep cloud SMS gateway as a fallback path |
| OCR misreads panel font | Validate against real panel footage ASAP in Week 2-3, not just synthetic tests |
| False triggers from glare | Debounce (2-3 frame) + anti-glare hardware already in design; test under real lighting |
| Module interfaces drift | Freeze data contracts (event object, DB schema, function signatures) at Week 4 checkpoint |
| Integration left too late | First full integration attempt scheduled Week 5, not Week 7 |

Final Deliverables Checklist

●  
      Working end-to-end pipeline running unattended on the Raspberry Pi

●  
      Calibration config + contact-mapping table for the installed panel

●  
      Permanent event log with a completed multi-day soak test

●  
      Updated proposal / as-built documentation

●  
      Final demo to stakeholders